## Risk Register
|  |  | Risk Register | [7 empty] | PAPER E
|  |  | ELRIUC |  | Start Date:02/10/18
Last Updated: 20.01.19
Risk Ref | Category | Internal / External | Risk Description | Cause | Date Raised | Owner | Likelihood | Consequence | Risk Score | Mitigation Plans | Controls in Place | Comments | Review Date | Open / Closed
R001 | Workforce | Internal | Inability to recruit workforce through lack of available resources in the market - in particular re. Prescribing Practitioners | External factors | 2018-10-02 | Simon Harris | 4 | 4 | 16 | Utilisation of agency workers whilst continued recruitment programme. Establish internal bank of staff. | Review & utilisation of existing DHU LLR workforce Review at weekly programme meetings as with all risks | None | 2019-01-21 | Open
R002 | Workforce | Internal | Lack of Staff to TUPE transfer and recruitment and retention of new staff | There is a risk that TUPE staff will choose not to transfer across and that staff may not be recruited in time leading to demand from the new contract not being met. | 2018-10-02 | Lisa Wallis | 4 | 4 | 16 | Specified HR resource to mange TUPE process - ensuring maximum engagement with TUPE colleagues. DHU has a rolling programme of recruitment and training to ensure that there are a sufficient number of available employees to meet the demands of the service. This rolling programme will continue until such time that the contract has been awarded. | Weekly programme checkpoint meeting to review level of risk and current status of TUPE staff. DHU will review this risk on a weekly basis and take steps to ensure that this does not pose a clinical risk to service delivery following Go Live date for the Contract. | None | 2019-01-21 | Open
R003 | Workforce | Internal | Incorrect or Incomplete TUPE information received prior to ITT submission | There is a risk that additional costs including salaries, redundancies, and pensions may not have been factored into the tender pricing leading to unexpected costs and budgetary challenges | 2018-10-02 | Lisa Wallis | 3 | 3 | 9 | Additional funds included in the tender to allow for unexpected costs. | Weekly programme checkpoint meetings to review financial performance and the impact of any further TUPE data as and when provided. funds included in the tender to allow for unexpected costs. | None | 2019-01-21 | Open
R004 | Workforce | Internal | Inability to achieve the desired Skillmix | External factors | 2018-10-02 | Simon Harris/ Saurabh Johri | 4 | 4 | 16 | Utilisation of agency workers whilst continued recruitment programme. Establish internal bank of staff. Short term additional use of GPs | Review & utilisation of existing DHU LLR workforce Review at weekly programme meetings as with all risks | None | 2019-01-21 | Open
R005 | Workforce | Internal | Failure to fully adopt or embed new Ways of working - new models of care. | There is a risk that engagement & training and their understanding of requirements in insufficient. | 2018-10-02 | Simon Harris/ Saurabh Johri | 3 | 4 | 12 | We have engaged additional clinical & operational support to assist with mobilisation. Establishment of regular staff engagement events. | Comms & Engagement as part of mobilisation plan. Delivery additional oversight / audit / compliance of process from "go live" | None | 2019-01-21 | Open
R008 | Equipment | Internal | Inability to deliver care to patients | inability to procure required equipment within required timescales | 2018-10-02 | Simon Harris/ Saurabh Johri | 2 | 4 | 8 | Potential transference of assets from existing provider. | Review at weekly programme meetings. | None | 2019-01-21 | Open
R010 | IT | Internal | Inability to record a contemporaneous record of care delivered. | Inability to procure the required S1 Community Unit within required timescales. Inability to activate the clinical system within the required timescales. Inability to sufficient train and engage colleagues to utilise the systems. | 2018-10-02 | Nat Pearson | 4 | 5 | 20 | implement manual systems. And / or Explore use of an existing S1 unit. | Review at weekly programme meetings. | None | 2019-01-21 | Open
R011 | Legal | Both | Activity exceeds contract volumes. | Unmet patient demand or inaccurate modelling of demand. | 2018-10-02 | Simon Harris | 3 | 4 | 12 | To mitigate this risk close forecasting dialogue with Commissioners will be the norm with historic and trend data shared to assess impact on the service, performance and system-wide implications. Regular demand and capacity profiling activity and contract thresholds for review. | Primary care bounce-back protocols in place. Partnership board and Governance structure to support demand management. Review at weekly programme meetings as with all risks | None | 2019-01-21 | Open
R012 | Legal | Both | Activity significantly less than contract volumes. | Reduction or diversion of patient demand. | 2018-10-02 | Simon Harris | 3 | 4 | 12 | To mitigate this risk close forecasting dialogue with Commissioners will be the norm with historic and trend data shared to assess impact on the service, performance and system-wide implications. Marketing plan for services, development of pathways with EMAS, primary and secondary care. | Partnership board and Governance structure to support demand management. Review at weekly programme meetings as with all risks | None | 2019-01-21 | Open
R013 | clinical & operational |  | Inability to meet patient need | unexpected surges in demand | 2018-10-02 | Dr Saurabh Johri | 4 | 3 | 12 | Screening of referrals - demand management of patients presenting or being referred. Communication plan relating to referrals from primary care | Capacity & demand monitoring tools. Reconfiguration of resource to match demand (within financial constraints) Contract Monitoring / Escalation | None | 2019-01-21 | Open
R014 | Clinical | Internal | Unidentified risk in delivering of new patient Pathways. | New Pathways with limited live testing prior to new service. | 2018-10-02 | Dr Saurabh Johri | 3 | 4 | 12 | Rapid Cycle Testing (PDSA). Phased roll-out. Strong local clinical leadership | Partnership board and Governance structure to ensure adequate testing, appropriate stakeholder engagement through the development of Pathways. Review at weekly programme meetings as with all risks | None | 2019-01-21 | Open
R015 | Workforce | Internal | Risk of staff absence at critical programme milestones due major illness affecting staff | There is a risk that a large number of DHU staff may be affected by a pandemic leading to a reduction in the staff available for Readiness Testing or affecting the number of staff available on shift for 'Go Live' date | 2018-10-02 | Simon Harris | 2 | 3 | 6 | Coverage as wide as possible to support reduced impact in case of pandemic and support staffing numbers required for shifts at all times. | Partnership board and Governance structure to support demand management. Review at weekly programme meetings as with all risks | None | 2019-01-21 | Open
R016 | Programme Risks | Internal | Insufficient internal resources available to deliver programme. | There is a risk that a lack of internal resources within DHU to deliver the programme will lead to slippage of milestones and delay in Service Readiness to go Live on 1st April 2019. | 2018-10-02 | Simon Harris | 3 | 4 | 12 | Risk will be mitigated as far as possible by appointing deputies to some Senior Management positions and also by having experienced Service Managers working in similar contracts across the organisation. DHU have engaged extra Interim resources to assist with programme work to ensure as far as possible that milestones are met on time. | Review at weekly programme meetings. | None | 2019-01-21 | Open
R017 | Programme Risks | Internal | Senior Management Leave and Sickness | There is a risk that programme tasks slippage due to annual leave and sickness of both DHU and Commissioners Team will lead to programme delays. | 2018-10-02 | Simon Harris | 1 | 4 | 4 | Careful planning for holidays will be undertaken when contract award is made. This risk can be mitigated by DHU Senior Management Deputies standing in the event of Holidays/sickness and also Commissioners. | Mitigation to be discussed at all programme review meetings and Deputies to be appointed for all Key programme Team members. | None | 2019-01-21 | Open
R018 | Operational | Internal | Enderby Leisure Centre Mobilisation | There is a risk that the new site @ Enderby Leisure Centre will not be delivered on time | 2019-01-14 | Simon Harris | 3 | 3 | 9 | Separate Task & Finish Group approach being taken with escalation & update provided to Mobilisation Group. Key elements of IT and construction currently on track with no flagged risk / delay | Review at weekly programme meetings. | None | 2019-01-21 | Open
R019 | Operational | Both | Higher than anticipated Walk In Volumes | inaccurate demand / capacity modelling due to high & "unpredictable" Walk In volumes - detail not provided through procurement. | 2019-01-17 | Simon Harris | 5 | 4 | 20 | To mitigate this risk close forecasting dialogue with Commissioners will be the norm Clear and agreed approach to progressive increase in the proportion of "booked" appointments Regular demand and capacity profiling activity and contract thresholds for review. | Review at weekly programme meetings as with all risks. Close Post Go live monitoring & data reporting | None | 2019-01-21 | Open
R020 | IT | Internal | lack of full electronic interoperability of booking pathways | Inability to implement suitably efficient and IG compliant, electronic appointment booking from EMIS Practices into S1 | 2019-01-12 | Nat Pearson | 4 | 4 | 16 | implement manual systems, as specificied within the the DHU ELR GP Fed Bid - mobilise a telephone booking option for EMIS practices, while contnuing to explore / await further developments in this area | Review at weekly programme meetings. | None | 2019-01-21 | Open
R021 | Financial | Both | Unplanned additional cost pressures identified post contract award | Inaccurate or unidentified costs arising post contract award - eg. Lease , drugs / prescribing | 2018-10-02 | Simon Harris | 4 | 4 | 16 | Additional funds included in the tender to allow for unexpected costs. | Weekly programme checkpoint meetings to review financial performance and the impact of any further TUPE data as and when provided. funds included in the tender to allow for unexpected costs. | None | 2019-01-21 | Open